{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Gantt","Back-end","About"],"not_rendered":{"charts":0,"images":3,"macros":1,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Gantt","index":0,"n_rows":103,"n_cols":64,"rows_kept":103,"cut":false,"hidden":false,"merged":[[4,1,4,7],[2,5,2,6],[1,8,1,11],[1,13,1,16],[2,2,2,4],[3,2,3,4],[1,34,1,37],[2,34,2,39],[1,23,1,26],[1,28,1,31],[1,18,1,21]]}
["Create a Gantt Chart in this worksheet.\nEnter title of this project in cell B1. \nLegend title is in cell I1.\nInformation about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet.\nContinue navigating down column A to hear further instructions.",null,null,null,null,null,null,null,"Legend:"]
["Enter Company Name in cell B2.\nA legend is in cells I2 through AC2.","NAAM",null,null,null,null,null,null,"schuren",null,null,null,null,"verfen",null,null,null,null,"Lakken",null,null,null,null,"Menien",null,null,null,null,"coaten",null,null,null,null,null,"logistiek"]
["Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table.  \nProject Start Date: label is in cell D3.","SUB NAAM","startdatum winteronderhoud",null,null,"2018-11-17",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"droog/wacht stap"]
["A Scrolling Increment is in cell F4. \nMonths for the dates in row 5 are displayed starting in cells I4 through cell BL4.\nDo not modify these cells. They are auto updated based on the project start date in cell F3.",null,"afwijking",null,null,0,null,null,{"$f":"TEXT(I5,\"mmmm\")","v":"november"},null,null,null,null,null,null,{"$f":"IF(TEXT(P5,\"mmmm\")=I4,\"\",TEXT(P5,\"mmmm\"))","v":""},null,null,null,null,null,null,{"$f":"IF(OR(TEXT(W5,\"mmmm\")=P4,TEXT(W5,\"mmmm\")=I4),\"\",TEXT(W5,\"mmmm\"))","v":"december"},null,null,null,null,null,null,{"$f":"IF(OR(TEXT(AD5,\"mmmm\")=W4,TEXT(AD5,\"mmmm\")=P4,TEXT(AD5,\"mmmm\")=I4),\"\",TEXT(AD5,\"mmmm\"))","v":""},null,null,null,null,null,null,{"$f":"IF(OR(TEXT(AK5,\"mmmm\")=AD4,TEXT(AK5,\"mmmm\")=W4,TEXT(AK5,\"mmmm\")=P4,TEXT(AK5,\"mmmm\")=I4),\"\",TEXT(AK5,\"mmmm\"))","v":""},null,null,null,null,null,null,{"$f":"IF(OR(TEXT(AR5,\"mmmm\")=AK4,TEXT(AR5,\"mmmm\")=AD4,TEXT(AR5,\"mmmm\")=W4,TEXT(AR5,\"mmmm\")=P4),\"\",TEXT(AR5,\"mmmm\"))","v":""},null,null,null,null,null,null,{"$f":"IF(OR(TEXT(AY5,\"mmmm\")=AR4,TEXT(AY5,\"mmmm\")=AK4,TEXT(AY5,\"mmmm\")=AD4,TEXT(AY5,\"mmmm\")=W4),\"\",TEXT(AY5,\"mmmm\"))","v":""},null,null,null,null,null,null,{"$f":"IF(OR(TEXT(BF5,\"mmmm\")=AY4,TEXT(BF5,\"mmmm\")=AR4,TEXT(BF5,\"mmmm\")=AK4,TEXT(BF5,\"mmmm\")=AD4),\"\",TEXT(BF5,\"mmmm\"))","v":"januari"}]
["Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated.\nDo not modify these cells.\nToday's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule.",null,null,null,null,null,null,null,{"$f":"IFERROR(Project_Start+Scrolling_Increment,TODAY())","v":"2018-11-17"},{"$f":"I5+1","v":"2018-11-18"},{"$f":"J5+1","v":"2018-11-19"},"2018-11-20","2018-11-21","2018-11-22","2018-11-23",{"$f":"O5+1","v":"2018-11-24"},{"$f":"P5+1","v":"2018-11-25"},"2018-11-26","2018-11-27","2018-11-28","2018-11-29","2018-11-30",{"$f":"V5+1","v":"2018-12-01"},{"$f":"W5+1","v":"2018-12-02"},"2018-12-03","2018-12-04","2018-12-05","2018-12-06","2018-12-07",{"$f":"AC5+1","v":"2018-12-08"},{"$f":"AD5+1","v":"2018-12-09"},"2018-12-10","2018-12-11","2018-12-12","2018-12-13","2018-12-14",{"$f":"AJ5+1","v":"2018-12-15"},{"$f":"AK5+1","v":"2018-12-16"},"2018-12-17","2018-12-18","2018-12-19","2018-12-20","2018-12-21",{"$f":"AQ5+1","v":"2018-12-22"},{"$f":"AR5+1","v":"2018-12-23"},"2018-12-24","2018-12-25","2018-12-26","2018-12-27","2018-12-28",{"$f":"AX5+1","v":"2018-12-29"},{"$f":"AY5+1","v":"2018-12-30"},{"$f":"AZ5+1","v":"2018-12-31"},"2019-01-01","2019-01-02","2019-01-03","2019-01-04",{"$f":"BE5+1","v":"2019-01-05"},{"$f":"BF5+1","v":"2019-01-06"},{"$f":"BG5+1","v":"2019-01-07"},"2019-01-08","2019-01-09","2019-01-10","2019-01-11"]
["A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. \nTo jump forward or backward in the timeline, enter a value of 0 or higher in cell F4.\nA value of 0 takes you to the beginning of the chart."]
["This row contains headers for the project schedule that follows below them. \nNavigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7.\nAll project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table.","omschrijving","Categorie","Boot","Voortgang","Start","Aantal dagen",null,{"$f":"LEFT(TEXT(I5,\"ddd\"),1)","v":"z"},{"$f":"LEFT(TEXT(J5,\"ddd\"),1)","v":"z"},"m","d","w","d","v","z","z","m","d","w","d","v","z","z","m","d","w","d","v","z","z","m","d","w","d","v","z","z","m","d","w","d","v","z",{"$f":"LEFT(TEXT(AS5,\"ddd\"),1)","v":"z"},"m","d","w","d","v","z","z","m","d","w","d","v","z","z","m","d","w","d","v"]
["Enter Project information starting in cell B9 through cell G9. \nSample data is in cells B9 through G33.\nEnter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting.\nThe next instruction is in cell A34.","Boot  naar loods","Logistiek",686,null,"2018-11-17",6,null,{"$f":"IF(AND($C8=\"logistiek\",I$5>=$F8,I$5<=$F8+$G8-1),2,IF(AND($C8=\"Drogen\",I$5>=$F8,I$5<=$F8+$G8-1),1,\"\"))","v":2},{"$f":"IF(AND($C8=\"logistiek\",J$5>=$F8,J$5<=$F8+$G8-1),2,IF(AND($C8=\"Drogen\",J$5>=$F8,J$5<=$F8+$G8-1),1,\"\"))","v":2},2,2,2,2,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Boot strippen","Logistiek",686,null,"2018-11-17",1,null,{"$f":"IF(AND($C9=\"logistiek\",I$5>=$F9,I$5<=$F9+$G9-1),2,IF(AND($C9=\"Drogen\",I$5>=$F9,I$5<=$F9+$G9-1),1,\"\"))","v":2},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Onderkant krabben+schuren","Schuren",686,null,"2018-11-22",3,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"bottomcoaten","coaten",686,null,"2018-11-24",4,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Menieen","menien",686,null,"2018-11-27",2,null,"","","","","",{"$f":"IF(AND($C12=\"logistiek\",N$5>=$F12,N$5<=$F12+$G12-1),2,IF(AND($C12=\"Drogen\",N$5>=$F12,N$5<=$F12+$G12-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C12=\"logistiek\",AS$5>=$F12,AS$5<=$F12+$G12-1),2,IF(AND($C12=\"Drogen\",AS$5>=$F12,AS$5<=$F12+$G12-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","",{"$f":"IF(AND($C12=\"logistiek\",BI$5>=$F12,BI$5<=$F12+$G12-1),2,IF(AND($C12=\"Drogen\",BI$5>=$F12,BI$5<=$F12+$G12-1),1,\"\"))","v":""},"","",""]
[null,"bottomcoaten","coaten",686,null,"2018-11-29",2,null,"",{"$f":"IF(AND($C13=\"logistiek\",J$5>=$F13,J$5<=$F13+$G13-1),2,IF(AND($C13=\"Drogen\",J$5>=$F13,J$5<=$F13+$G13-1),1,\"\"))","v":""},"","","","","","","","","","","","","","",{"$f":"IF(AND($C13=\"logistiek\",Y$5>=$F13,Y$5<=$F13+$G13-1),2,IF(AND($C13=\"Drogen\",Y$5>=$F13,Y$5<=$F13+$G13-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","",{"$f":"IF(AND($C13=\"logistiek\",AO$5>=$F13,AO$5<=$F13+$G13-1),2,IF(AND($C13=\"Drogen\",AO$5>=$F13,AO$5<=$F13+$G13-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","",""]
[null,"dorgen","drogen",686,null,"2018-11-30",1,null,"","","","","","","","","","","","","",{"$f":"IF(AND($C14=\"logistiek\",V$5>=$F14,V$5<=$F14+$G14-1),2,IF(AND($C14=\"Drogen\",V$5>=$F14,V$5<=$F14+$G14-1),1,\"\"))","v":1},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Binnenkant schuren","Schuren",686,null,"2018-12-01",1,null,"","","","","","","","","","","","","",{"$f":"IF(AND($C15=\"logistiek\",V$5>=$F15,V$5<=$F15+$G15-1),2,IF(AND($C15=\"Drogen\",V$5>=$F15,V$5<=$F15+$G15-1),1,\"\"))","v":""},"","",{"$f":"IF(AND($C15=\"logistiek\",Y$5>=$F15,Y$5<=$F15+$G15-1),2,IF(AND($C15=\"Drogen\",Y$5>=$F15,Y$5<=$F15+$G15-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Menieen","menien",686,null,"2018-12-01",6,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"draaien","Logistiek",686,null,"2018-12-01",1,null,"","","","","","","","","","","","","","",2,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Blauwen","verfen",686,null,"2018-12-06",2,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"blauwen","verfen",686,null,"2018-12-08",6,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"schuren","Schuren",686,null,"2018-12-08",1,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"gele rand","verfen",686,null,"2018-12-13",2,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"drogen","drogen",686,null,"2018-12-14",2,null,"",{"$f":"IF(AND($C22=\"logistiek\",J$5>=$F22,J$5<=$F22+$G22-1),2,IF(AND($C22=\"Drogen\",J$5>=$F22,J$5<=$F22+$G22-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","",1,1,"","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Boot  naar loods","Logistiek",872,null,"2018-11-17",6,null,{"$f":"IF(AND($C23=\"logistiek\",I$5>=$F23,I$5<=$F23+$G23-1),2,IF(AND($C23=\"Drogen\",I$5>=$F23,I$5<=$F23+$G23-1),1,\"\"))","v":2},2,2,2,2,2,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Boot strippen","Logistiek",872,null,"2018-11-17",1,null,2,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Onderkant krabben+schuren","Schuren",872,null,"2018-11-22",3,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"bottomcoaten","coaten",872,null,"2018-11-24",4,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C26=\"logistiek\",BH$5>=$F26,BH$5<=$F26+$G26-1),2,IF(AND($C26=\"Drogen\",BH$5>=$F26,BH$5<=$F26+$G26-1),1,\"\"))","v":""},"","","",""]
[null,"Menieen","menien",872,null,"2018-11-27",2,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"bottomcoaten","coaten",872,null,"2018-11-29",2,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"dorgen","drogen",872,null,"2018-11-30",1,null,"","","","","","","","","","","","","",1,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Binnenkant schuren","Schuren",872,null,"2018-12-01",1,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Menieen","menien",872,null,"2018-12-01",6,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C31=\"logistiek\",AN$5>=$F31,AN$5<=$F31+$G31-1),2,IF(AND($C31=\"Drogen\",AN$5>=$F31,AN$5<=$F31+$G31-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"draaien","Logistiek",872,null,"2018-12-01",1,null,"","","","","","","","","","","","","","",2,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"Blauwen","verfen",872,null,"2018-12-06",2,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"blauwen","verfen",872,null,"2018-12-08",6,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"schuren","Schuren",872,null,"2018-12-08",1,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"gele rand","verfen",872,null,"2018-12-13",2,null,"","","","","","","","","","","",{"$f":"IF(AND($C36=\"logistiek\",T$5>=$F36,T$5<=$F36+$G36-1),2,IF(AND($C36=\"Drogen\",T$5>=$F36,T$5<=$F36+$G36-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,"drogen","drogen",872,null,"2018-12-14",3,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","",1,1,1,"","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,"Logistiek","Houtwerk",null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C40=\"logistiek\",BC$5>=$F40,BC$5<=$F40+$G40-1),2,IF(AND($C40=\"Drogen\",BC$5>=$F40,BC$5<=$F40+$G40-1),1,\"\"))","v":""},"","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C45=\"logistiek\",AI$5>=$F45,AI$5<=$F45+$G45-1),2,IF(AND($C45=\"Drogen\",AI$5>=$F45,AI$5<=$F45+$G45-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","",{"$f":"IF(AND($C50=\"logistiek\",O$5>=$F50,O$5<=$F50+$G50-1),2,IF(AND($C50=\"Drogen\",O$5>=$F50,O$5<=$F50+$G50-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C54=\"logistiek\",AX$5>=$F54,AX$5<=$F54+$G54-1),2,IF(AND($C54=\"Drogen\",AX$5>=$F54,AX$5<=$F54+$G54-1),1,\"\"))","v":""},"","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C59=\"logistiek\",AD$5>=$F59,AD$5<=$F59+$G59-1),2,IF(AND($C59=\"Drogen\",AD$5>=$F59,AD$5<=$F59+$G59-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"",{"$f":"IF(AND($C64=\"logistiek\",J$5>=$F64,J$5<=$F64+$G64-1),2,IF(AND($C64=\"Drogen\",J$5>=$F64,J$5<=$F64+$G64-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C68=\"logistiek\",AS$5>=$F68,AS$5<=$F68+$G68-1),2,IF(AND($C68=\"Drogen\",AS$5>=$F68,AS$5<=$F68+$G68-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","",{"$f":"IF(AND($C73=\"logistiek\",Y$5>=$F73,Y$5<=$F73+$G73-1),2,IF(AND($C73=\"Drogen\",Y$5>=$F73,Y$5<=$F73+$G73-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C77=\"logistiek\",BH$5>=$F77,BH$5<=$F77+$G77-1),2,IF(AND($C77=\"Drogen\",BH$5>=$F77,BH$5<=$F77+$G77-1),1,\"\"))","v":""},"","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C82=\"logistiek\",AN$5>=$F82,AN$5<=$F82+$G82-1),2,IF(AND($C82=\"Drogen\",AN$5>=$F82,AN$5<=$F82+$G82-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,{"$f":"IF(AND($C87=\"logistiek\",I$5>=$F87,I$5<=$F87+$G87-1),2,IF(AND($C87=\"Drogen\",I$5>=$F87,I$5<=$F87+$G87-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C87=\"logistiek\",AI$5>=$F87,AI$5<=$F87+$G87-1),2,IF(AND($C87=\"Drogen\",AI$5>=$F87,AI$5<=$F87+$G87-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","",{"$f":"IF(AND($C92=\"logistiek\",O$5>=$F92,O$5<=$F92+$G92-1),2,IF(AND($C92=\"Drogen\",O$5>=$F92,O$5<=$F92+$G92-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C96=\"logistiek\",AX$5>=$F96,AX$5<=$F96+$G96-1),2,IF(AND($C96=\"Drogen\",AX$5>=$F96,AX$5<=$F96+$G96-1),1,\"\"))","v":""},"","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","",{"$f":"IF(AND($C101=\"logistiek\",AD$5>=$F101,AD$5<=$F101+$G101-1),2,IF(AND($C101=\"Drogen\",AD$5>=$F101,AD$5<=$F101+$G101-1),1,\"\"))","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
["This is an empty row",null,null,null,null,null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
["This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. \nTo add more items, insert new rows above this one.","To add more data, Insert new rows ABOVE this one"]

{"sheet":"Back-end","index":1,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":false,"merged":[]}
["types","Boten"]
["Logistiek",4]
["Schuren",109]
["verfen",686]
["lakken",872]
["menien",926]
["drogen",1005]
["coaten",1049]
[null,1449]
[null,1450]
[null,"MV"]
[null,"ALL"]
[null,"Houtwerk"]

{"sheet":"About","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}